## PROJECT PARAMETERS
[Company Name]
Event Management Project Tracker
Company Confidential
Shaded cells are calculated for you. You do not need to enter anything into them.
PROJECT TYPE | ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF | Total
Event strategy development | 20% | 10% | 60% | 0% | 0% | 10% | 100%
Event planning | 20% | 50% | 10% | 10% | 0% | 10% | 100%
Event design | 20% | 20% | 0% | 50% | 0% | 10% | 100%
Event logistics | 20% | 60% | 0% | 0% | 10% | 10% | 100%
Event staffing | 20% | 10% | 0% | 0% | 60% | 10% | 100%
Event assessment | 20% | 20% | 20% | 20% | 0% | 20% | 100%
Blended rates | 180 | 120 | 150 | 100 | 80 | 60
| ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF
PLANNED COST | 272340 | 319320 | 123450 | 106000 | 49320 | 53490
ACTUAL COST | 273960 | 324540 | 126150 | 104950 | 48160 | 53460
PLANNED HOURS | 1513 | 1774 | 685.8333 | 588.8889 | 274 | 297.1667
ACTUAL HOURS | 1522 | 1803 | 700.8333 | 583.0556 | 267.5556 | 297

## PROJECT DETAILS
[Company Name]
Event Management Project Tracker
Company Confidential
[10 empty] | PLANNING | [5 empty] | ACTUALS
PROJECT NAME | PROJECT TYPE | ESTIMATED START | ESTIMATED FINISH | ACTUAL START | ACTUAL FINISH | ESTIMATED WORK | ACTUAL WORK | ESTIMATED DURATION | ACTUAL DURATION | ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF | ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF
A. Datum Corporation | Event strategy development | 2013-06-09 | 2013-08-07 | 2013-06-29 | 2013-09-03 | 200 | 220 | 58 | 64 | 7200 | 2400 | 18000 | 0 | 0 | 1200 | 7920 | 2640 | 19800 | 0 | 0 | 1320
Adventure Works | Event planning | 2013-06-25 | 2013-07-27 | 2013-07-15 | 2013-08-25 | 400 | 390 | 32 | 40 | 14400 | 24000 | 6000 | 4000 | 0 | 2400 | 14040 | 23400 | 5850 | 3900 | 0 | 2340
Alpine Ski House | Event design | 2013-07-12 | 2013-09-19 | 2013-08-07 | 2013-10-10 | 500 | 500 | 67 | 63 | 18000 | 12000 | 0 | 25000 | 0 | 3000 | 18000 | 12000 | 0 | 25000 | 0 | 3000
Baldwin Museum of Science | Event logistics | 2013-07-30 | 2013-09-28 | 2013-09-14 | 2013-11-13 | 150 | 145 | 58 | 59 | 5400 | 10800 | 0 | 0 | 1200 | 900 | 5220 | 10440 | 0 | 0 | 1160 | 870
Blue Yonder Airlines | Event staffing | 2013-08-11 | 2013-08-21 | 2013-09-14 | 2013-09-25 | 250 | 255 | 10 | 11 | 9000 | 3000 | 0 | 0 | 12000 | 1500 | 9180 | 3060 | 0 | 0 | 12240 | 1530
City Power & Light | Event assessment | 2013-08-22 | 2013-10-02 | 2013-09-28 | 2013-10-27 | 300 | 310 | 40 | 29 | 10800 | 7200 | 9000 | 6000 | 0 | 3600 | 11160 | 7440 | 9300 | 6200 | 0 | 3720
Coho Vineyard | Event planning | 2013-09-13 | 2013-09-23 | 2013-10-26 | 2013-10-13 | 500 | 510 | 10 | -13 | 18000 | 30000 | 7500 | 5000 | 0 | 3000 | 18360 | 30600 | 7650 | 5100 | 0 | 3060
Coho Winery | Event logistics | 2013-09-21 | 2013-10-15 | 2013-10-23 | 2013-11-18 | 750 | 790 | 24 | 25 | 27000 | 54000 | 0 | 0 | 6000 | 4500 | 28440 | 56880 | 0 | 0 | 6320 | 4740
Coho Vineyard & Winery | Event assessment | 2013-10-15 | 2013-11-25 | 2013-11-30 | 2014-01-10 | 450 | 430 | 40 | 40 | 16200 | 10800 | 13500 | 9000 | 0 | 5400 | 15480 | 10320 | 12900 | 8600 | 0 | 5160
Contoso, Ltd. | Event staffing | 2013-10-26 | 2013-12-24 | 2013-11-26 | 2014-01-19 | 250 | 235 | 58 | 53 | 9000 | 3000 | 0 | 0 | 12000 | 1500 | 8460 | 2820 | 0 | 0 | 11280 | 1410
Contoso Pharmaceuticals | Event planning | 2013-11-17 | 2014-01-15 | 2013-12-28 | 2014-02-26 | 200 | 235 | 58 | 58 | 7200 | 12000 | 3000 | 2000 | 0 | 1200 | 8460 | 14100 | 3525 | 2350 | 0 | 1410
Consolidated Messenger | Event strategy development | 2013-12-03 | 2014-02-02 | 2014-01-14 | 2014-03-02 | 180 | 190 | 59 | 48 | 6480 | 2160 | 16200 | 0 | 0 | 1080 | 6840 | 2280 | 17100 | 0 | 0 | 1140
Fabrikam, Inc. | Event staffing | 2013-06-21 | 2014-01-18 | 2013-08-05 | 2014-03-04 | 250 | 230 | 207 | 209 | 9000 | 3000 | 0 | 0 | 12000 | 1500 | 8280 | 2760 | 0 | 0 | 11040 | 1380
Fourth Coffee | Event logistics | 2013-12-20 | 2014-02-04 | 2014-01-27 | 2014-03-25 | 240 | 225 | 44 | 58 | 8640 | 17280 | 0 | 0 | 1920 | 1440 | 8100 | 16200 | 0 | 0 | 1800 | 1350
Graphic Design Institute | Event design | 2013-12-28 | 2014-03-05 | 2014-01-17 | 2014-04-10 | 320 | 305 | 67 | 83 | 11520 | 7680 | 0 | 16000 | 0 | 1920 | 10980 | 7320 | 0 | 15250 | 0 | 1830
Humongous Insurance | Event planning | 2014-01-04 | 2014-03-06 | 2014-02-03 | 2014-04-06 | 550 | 565 | 62 | 63 | 19800 | 33000 | 8250 | 5500 | 0 | 3300 | 20340 | 33900 | 8475 | 5650 | 0 | 3390
Litware, Inc. | Event design | 2014-01-23 | 2014-03-07 | 2014-03-07 | 2014-04-08 | 350 | 350 | 44 | 31 | 12600 | 8400 | 0 | 17500 | 0 | 2100 | 12600 | 8400 | 0 | 17500 | 0 | 2100
Lucerne Publishing | Event strategy development | 2014-02-05 | 2014-04-17 | 2014-03-07 | 2014-06-03 | 200 | 205 | 72 | 86 | 7200 | 2400 | 18000 | 0 | 0 | 1200 | 7380 | 2460 | 18450 | 0 | 0 | 1230
Margie's Travel | Event planning | 2014-02-15 | 2014-04-30 | 2014-03-26 | 2014-06-09 | 220 | 230 | 75 | 73 | 7920 | 13200 | 3300 | 2200 | 0 | 1320 | 8280 | 13800 | 3450 | 2300 | 0 | 1380
Northwind Traders | Event assessment | 2014-03-17 | 2014-05-25 | 2014-04-29 | 2014-07-01 | 600 | 560 | 68 | 62 | 21600 | 14400 | 18000 | 12000 | 0 | 7200 | 20160 | 13440 | 16800 | 11200 | 0 | 6720
Proseware, Inc. | Event logistics | 2014-03-29 | 2014-05-19 | 2014-05-18 | 2014-06-19 | 525 | 540 | 50 | 31 | 18900 | 37800 | 0 | 0 | 4200 | 3150 | 19440 | 38880 | 0 | 0 | 4320 | 3240
School of Fine Art | Event planning | 2014-04-09 | 2014-04-29 | 2014-05-02 | 2014-06-04 | 180 | 190 | 20 | 32 | 6480 | 10800 | 2700 | 1800 | 0 | 1080 | 6840 | 11400 | 2850 | 1900 | 0 | 1140
TOTAL | [5 empty] | 7565 | 7610 | 1223 | 1205
INFO
To add a row, select the bottom-right most cell in the body of the table (not the totals row) and press Tab, or right-click where you want the row inserted and select Insert | Table Rows Above/Below.
Be sure all unused rows are deleted, as the PROJECT TOTALS PivotTable will use all of the tables cells, and otherwise would give erroneous results.
To delete this info tip, select any edge and press Delete.

## PROJECT TOTALS
[Company Name]
Event Management Project Tracker
Company Confidential
PROJECT NAME | ACCOUNT MANAGER ESTIMATE | PROJECT MANAGER ESTIMATE | STRATEGY MANAGER ESTIMATE | DESIGN SPECIALIST ESTIMATE | EVENT STAFF ESTIMATE | ADMIN STAFF ESTIMATE | ACCOUNT MANAGER ACTUAL | PROJECT MANAGER ACTUAL | STRATEGY MANAGER ACTUAL | DESIGN SPECIALIST ACTUAL | EVENT STAFF ACTUAL | ADMIN STAFF ACTUAL
A. Datum Corporation | 7200 | 2400 | 18000 | 0 | 0 | 1200 | 7920 | 2640 | 19800 | 0 | 0 | 1320
Adventure Works | 14400 | 24000 | 6000 | 4000 | 0 | 2400 | 14040 | 23400 | 5850 | 3900 | 0 | 2340
Alpine Ski House | 18000 | 12000 | 0 | 25000 | 0 | 3000 | 18000 | 12000 | 0 | 25000 | 0 | 3000
Baldwin Museum of Science | 5400 | 10800 | 0 | 0 | 1200 | 900 | 5220 | 10440 | 0 | 0 | 1160 | 870
Blue Yonder Airlines | 9000 | 3000 | 0 | 0 | 12000 | 1500 | 9180 | 3060 | 0 | 0 | 12240 | 1530
City Power & Light | 10800 | 7200 | 9000 | 6000 | 0 | 3600 | 11160 | 7440 | 9300 | 6200 | 0 | 3720
Coho Vineyard | 18000 | 30000 | 7500 | 5000 | 0 | 3000 | 18360 | 30600 | 7650 | 5100 | 0 | 3060
Coho Vineyard & Winery | 16200 | 10800 | 13500 | 9000 | 0 | 5400 | 15480 | 10320 | 12900 | 8600 | 0 | 5160
Coho Winery | 27000 | 54000 | 0 | 0 | 6000 | 4500 | 28440 | 56880 | 0 | 0 | 6320 | 4740
Consolidated Messenger | 6480 | 2160 | 16200 | 0 | 0 | 1080 | 6840 | 2280 | 17100 | 0 | 0 | 1140
Contoso Pharmaceuticals | 7200 | 12000 | 3000 | 2000 | 0 | 1200 | 8460 | 14100 | 3525 | 2350 | 0 | 1410
Contoso, Ltd. | 9000 | 3000 | 0 | 0 | 12000 | 1500 | 8460 | 2820 | 0 | 0 | 11280 | 1410
Fabrikam, Inc. | 9000 | 3000 | 0 | 0 | 12000 | 1500 | 8280 | 2760 | 0 | 0 | 11040 | 1380
Fourth Coffee | 8640 | 17280 | 0 | 0 | 1920 | 1440 | 8100 | 16200 | 0 | 0 | 1800 | 1350
Graphic Design Institute | 11520 | 7680 | 0 | 16000 | 0 | 1920 | 10980 | 7320 | 0 | 15250 | 0 | 1830
Humongous Insurance | 19800 | 33000 | 8250 | 5500 | 0 | 3300 | 20340 | 33900 | 8475 | 5650 | 0 | 3390
Litware, Inc. | 12600 | 8400 | 0 | 17500 | 0 | 2100 | 12600 | 8400 | 0 | 17500 | 0 | 2100
Lucerne Publishing | 7200 | 2400 | 18000 | 0 | 0 | 1200 | 7380 | 2460 | 18450 | 0 | 0 | 1230
Margie's Travel | 7920 | 13200 | 3300 | 2200 | 0 | 1320 | 8280 | 13800 | 3450 | 2300 | 0 | 1380
Northwind Traders | 21600 | 14400 | 18000 | 12000 | 0 | 7200 | 20160 | 13440 | 16800 | 11200 | 0 | 6720
Proseware, Inc. | 18900 | 37800 | 0 | 0 | 4200 | 3150 | 19440 | 38880 | 0 | 0 | 4320 | 3240
School of Fine Art | 6480 | 10800 | 2700 | 1800 | 0 | 1080 | 6840 | 11400 | 2850 | 1900 | 0 | 1140
Grand Total | 272340 | 319320 | 123450 | 106000 | 49320 | 53490 | 273960 | 324540 | 126150 | 104950 | 48160 | 53460
INFO
This PivotTable will not refresh automatically. To refresh it, select it (any cell within the PivotTable), on the PIVOTTABLE TOOLS | ANALYZE ribbon tab press Refresh. Or right-click any cell in the PivotTable and select Refresh.
To delete this info tip, select any edge and press Delete.