## Project Workplan
Project Plan mnüu
| Date of Report | 2005-06-30
| Name | Client Performance Management System | [5 empty] | Sponsor | Bill Praxton, CFO
| Description | The Cost Accounting project in support of the cost build-up requirement for the DoD IG proposal.
| Start Date | 2004-10-01 |  |  |  | End Date |  | 2006-03-28
Balanced Scorecard Design and Development Plan
Item No | Task |  | Actual Start Date | Tentative Start Date | Impact on Completion (Actual vs. Target) | Target Completion date & Status |  | Comments |  |  |  | Deliverables | Lead
| 1. Refresh the Strategic Plan |  | 2004-12-01 |  |  | 2005-04-30
1.1 | Review current strategic planning documents and determine if the current plan is appropriate for the Balanced Scorecard |  | 2004-11-15 |  |  | 2005-03-31 | n
1.2 | Prepare for Strategic Planning Off-site |  | 2005-02-01 |  |  | 2005-04-15 | ü
1.3 | Strategic Planning working group to develop draft revised Strategic Plan - See Planning Workshop Coordinator for more details |  | 2005-03-22 |  |  |  | m |  |  |  |  | 1) Kick off meeting of technical group
1.4 | Senior Leadership approves revised Strategic Plan |  | After Phase 3 |  |  |  | m
1.5 | Communicate Strategic Plan and Balanced Scorecard in printed and electronic format |  | After Phase 3 |  |  |  | m |  |  |  |  | 1) Strategic Plan booklet 2) Strategy Map Draft
| 2. Strategy Map / Strategic Plan |  | 2005-03-01
2.1 | Preliminary Draft Map with no extras for Gap Analysis only | [10 empty] | 3) Very Basic Strategy Map
2.2 | Isolate holes / gaps between draft strategic plan vs. Draft Strategy Map | [10 empty] | 4) Gap Analysis Results and recommendations to fill out S-Plan
2.3 | Make revisions to lower level objectives in Draft Strategic Plan and fill-out Strategy Map for all components - themes, narrative add-on's and complete cause-effect flows. | [10 empty] | 5) Revised Strategic Plan 6) Revised Strategy Map
2.4 | Approval of Revised Strategic Plan and Final and Complete Strategy Map | [6 empty] | May have to schedule at joint leadership off-site |  |  |  | 7) Briefing Session
2.5 | Develop Communication Plan for Strategic Plan | [10 empty] | 8) Communication Plan
2.6 | Launch Action Plan Steps for Strategic Plan with Strategy Map | [6 empty] | May require meetings and other events per the Communication Plan |  |  |  | 9) Action Plan for Communication Plan
2.7 | Centralize feedback and comments for next planning cycle. Collect and recommend for next planning session cycle. | [6 empty] | Output from this step does not get acted upon until next annual planning cycle. |  |  |  | 10) Feedback Collection System and Reports
3. Measurements and Targets
3.1 | Create measurement and target development workplan complete with templates and methodology | [10 empty] | 11) Performance measurement training, tools, methodology
3.2 | Quality control review to refine and improve complete measurement approach for client | [10 empty] | Final set of tools to development enterprise wide performance measurements
3.3 | Extend each objective on the Strategy Map into one to three performance measurements | [6 empty] | Follow the methodology and training
3.4 | Solicit input and feedback from functional leads and line and staff personnel | [10 empty] | Revised set of performance measurements
3.5 | Establish a set of targets in accordance with operational goals that are linked to the Strategic Plan | [10 empty] | Targets for each measurement
3.6 | Identify initiatives and projects related to execution of each objective. Extend the Map | [10 empty] | Scorecard Model
3.7 | Prototype test Scorecard Model for data points that use existing measurement data | [6 empty] | Make sure model is tight / fits across all components
3.8 | Complete a comprehensive measurement template for database development | [10 empty] | Performance measurement development template
4. Initiative Mapping and Budgeting
4.1 | Extend Initiative and Projects that are part of Scorecard Model into Action Plans or document with existing plans | [6 empty] | Extended Scorecard Model ensures execution of the Strategic Plan |  |  |  | Extended Scorecard Model
4.2 | Link the Initiative / Projects within the Scorecard Model to the Budgeting Process
4.3 | Identify gaps and short coming with linking and make recommendations to improve | [10 empty] | Recommended Changes to Link Processes Together
4.4 | Cross walk all major initiatives against the Strategic Objectives - Pareto Chart the initiatives / projects | [10 empty] | Graph of what should get resourced vs. what should not
4.5 | Work back upstream from initiatives / projects not linked and document any missing lower level objectives in strategic plan and / or strategy map | [10 empty] | Operating Plan / Sub Objective Additions
5. Reporting Framework (Database)
5.1 | Map and build a framework structure from the highest organizational level down to the managerial level | [6 empty] | See other similar models from other performance management projects |  |  |  | Visual prototype framework for review
5.2 | Align and link lower level components by through objective setting - upper to lower by organizational level / reporting units
5.3 | Assign performance measurements for lower level objectives. Index across common reporting units for the same objective.
5.4 | Complete a comprehensive measurement template for database development for this reporting level (lower objectives)
5.5 | Prototype test and revise database design of Balanced Scorecard System - (ESMS | [6 empty] | NOTE: The IT Design and Development Plan covers automation of the Enterprise Strategic Management System |  |  |  | Various automated tools, such as data collection forms, reporting tools, etc.
5.6 | Roll out test modules at pilot sites - flush out lessons learned and update IT Plans
5.7 | Cascade and development plan for Enterprise Strategic Management System (ESMS) | [10 empty] | ESMS Design and Development Plan
| Baseline End Date | [9 empty] | 2006-03-28
Major Issues
Item No. | Description |  |  |  |  | Comments |  |  |  |  | Status
1
2
3
4
Application Issues
| Description |  |  |  |  | Action Required By |  | Target Date | Confidence of Closure | Current Action
Process Issues
| Subject Area |  |  |  |  | Action Required By |  | Target Date | Confidence of Closure | Current Action
Resource Issues
| Subject Area |  |  |  |  | Action Required By |  | Target Date | Confidence of Closure | Current Action
Not Started m
On Plan n
Issues u
m Not started
n On Plan
ü Complete
u Issues
Complete ü

## Performance Measure Template
All Measurements Used in the ESMS Database
| PM # | Performance Measure | BSC Framework | Strategic Goal or Objective per BSC or Strategic Plan | Army Performance Improvement Criteria (APIC) - 7 Major Categories Summarized Below | Major Organizational Unit | Function / Dept / Sub Group | Service or Product Line (if applicable) | METL Task | METL Sub-Task | Type of Measure | Measure Justification | Definition | Data Elements To Be Collected | Data Source | Data Collection Frequency D/W/M/Q/SA/A | PM Calculation Formula | Actual FY 03 | Actual FY 04 | Green Standard | Amber Standard | Red Standard | Primary Functional POC | Data Available? | Notes
Definition | What is the PM number for referencing. Could be LMR # or a unique number for local metrics? | What metric(s) should we use to measure whether we have met our requirements? | Is this measure a Customer, Process, Learn & Grow or Resources measure based on the BSC framework? | Insert major goals or objectives in this box as a reference in completing this template | 1) Formal Systems to Learn and Grow People 2) All Key processes are adding value 3) Strong focus on Customer Needs 4) Strategic Planning Process in Place 5) Leadership Effectiveness 6) Well Developed PMR is Followed 7) Key Performance Results in Place | Insert a list of the major organizational unit names in this box for reference in completing this template | Insert a Link here to reference back a list of Functions / Departments and other organizational units in completing this template | Insert the Operating Area such as Product or Service Line - To be used for Product Performance Analysis | What METL Task does the metric support? | What METL Sub-task does the metric support? | Is this measure a 1) Strategic 2) Operational 3) Tactical 4) Individual | Why are we using this metric? | How do we define this measure? | What are the data elements for caclulating the measure? | Where does the data reside? | How frequently should the data be collected? | What is the formula for calculating the measure? | What is the actual result of this measure for the Year 2003? | What is the actual result of this measure for the Year 2004? | What is the Green Threshold? | What is the Amber Threshold? | What is the Red Threshold? | Who is the primary owner for the measure and their email address? | Y/N | Are there any additional notes regarding the measure?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
Note on M3: Measure Justification Criterial Meaningful: Measureable: Actionable: Input/Output/Outcome: Lead/Lag:

## Performance Measure Grading
Balanced Scorecard Project |  |  |  | Graded Attributes | Update Frequency / Repeatable | Degree of Reliability (Hard Data vs.Subjective) | Encourages the right behavior | Degree of Fit with Client's Culture | Degree of Support / Available Info |  |  | NonGraded Attributes | Leading or Lagging | Single or Index Metric
Quality Review of Metrics
Review and score all measurements used in your scorecard model | [9 empty] | Total Points | Overall Grade
Financial Objective (F1) | F1.1 | % Revenue Growth |  |  | 4 | 4 | 3 | 4 | 5 | 20 | 80% |  | Lagging | Single
| F1.2 | [8 empty] | 0 | 0%
| F1.3 | [8 empty] | 0 | 0%
| F1.4 | [8 empty] | 0 | 0%
Financial Objective (F2) | F2.1 | [8 empty] | 0 | 0%
| F2.2 | [8 empty] | 0 | 0%
| F2.3 | [8 empty] | 0 | 0%
| F2.4 | [8 empty] | 0 | 0%
Financial Objective (F3) | F3.1 | [8 empty] | 0 | 0%
| F3.2 | [8 empty] | 0 | 0%
| F3.3 | [8 empty] | 0 | 0%
| F3.4 | [8 empty] | 0 | 0%
Customer Objective (C1) | C1.1 | [8 empty] | 0 | 0%
| C1.2 | [8 empty] | 0 | 0%
| C1.3 | [8 empty] | 0 | 0%
| C1.4 | [8 empty] | 0 | 0%
Customer Objective (P2) | C2.1 | [8 empty] | 0 | 0%
| C2.2 | [8 empty] | 0 | 0%
| C2.3 | [8 empty] | 0 | 0%
| C2.4 | [8 empty] | 0 | 0%
Process Objective (P1) | P1.1 | [8 empty] | 0 | 0%
| P1.2 | [8 empty] | 0 | 0%
| P1.3 | [8 empty] | 0 | 0%
| P1.4 | [8 empty] | 0 | 0%
Process Objective (P2) | P2.1 | [8 empty] | 0 | 0%
| P2.2 | [8 empty] | 0 | 0%
| P2.3 | [8 empty] | 0 | 0%
| P2.4 | [8 empty] | 0 | 0%
Process Objective (P5) | P3.1 | [8 empty] | 0 | 0%
| P3.2 | [8 empty] | 0 | 0%
| P3.3 | [8 empty] | 0 | 0%
| P3.4 | [8 empty] | 0 | 0%
Process Objective (P4) | P4.1 | [8 empty] | 0 | 0%
| P4.2 | [8 empty] | 0 | 0%
| P4.3 | [8 empty] | 0 | 0%
| P4.4 | [8 empty] | 0 | 0%
L & G Objective (L1) | L1.1 | [8 empty] | 0 | 0%
| L1.2 | [8 empty] | 0 | 0%
| L1.3 | [8 empty] | 0 | 0%
| L1.4 | [8 empty] | 0 | 0%
L & G Objective (L2) | L2.1 | [8 empty] | 0 | 0%
| L2.2 | [8 empty] | 0 | 0%
| L2.3 | [8 empty] | 0 | 0%
| L2.4 | [8 empty] | 0 | 0%
L & G Objective (L3) | L3.1 | [8 empty] | 0 | 0%
| L3.2 | [8 empty] | 0 | 0%
| L3.3 | [8 empty] | 0 | 0%
| L3.4 | [8 empty] | 0 | 0%
Instructions:
Rate each Measurement for these attributes on a scale of 1 to 5:
1. Update Frequency: Measurement can get updated on a regular basis; M for Monthly, Q for Quarterly, A for Annual, etc.
2. Degree of Reliability: Can you easily measure the performance objective or is it too subjective when it comes to measurability.
3. Encourages the right behavior: Measurements should not confuse, distort, or create the wrong performance behavior within the Organization. Controllable?
4. Degree of Fit: Measurement fits with the culture and processes of Organization and flows well from Lower Level to Upper Level. (MACRO FIT - ORGANIZATIONAL)
5. Degree of Support: Client has existing procedures and processes that can support the measurement (such as available data is in place)
| Maximum Score |  | 25

## Powerpoint Slides
Alignment Matrix
Strategic
Drivers
Vision
Mission
Values
Critical
Processes
Measures
Critical
Levers
Organization
Measures
Tools

## Team List
Project Roster
Name | Area | Location | Desk Phone | Cell Phone | Email
Project Intranet Web Site ► | www.intranets.com