## PROJECT PARAMETERS
[Company Name]
Project Planning for Law Firms
Company Confidential
Shaded cells are calculated for you. You do not need to enter anything into them.
PROJECT TYPE | GENERAL PARTNER | BUSINESS LAWYER | DEFENSE LITIGATOR | INTELLECTUAL PROPERTY LAWYER | BANKRUPTCY LAWYER | ADMIN STAFF | TOTAL
Business Incorporation | 10% | 40% | 0% | 0% | 0% | 50% | 100%
Business Acquisition | 10% | 40% | 0% | 10% | 0% | 40% | 100%
Product Liability Defense | 20% | 0% | 50% | 0% | 0% | 30% | 100%
Patent Application | 10% | 0% | 0% | 60% | 0% | 30% | 100%
Employee Lawsuit | 20% | 10% | 40% | 0% | 0% | 30% | 100%
Bankruptcy | 10% | 20% | 0% | 0% | 40% | 30% | 100%
Blended rates | 350 | 250 | 300 | 275 | 225 | 125
| GENERAL PARTNER | BUSINESS | DEFENSE LITIGATOR | INTELLECTUAL PROP. | BANKRUPTCY | ADMIN STAFF
PLANNED COST | 339675 | 305250 | 301500 | 311300 | 151200 | 320562.5
ACTUAL COST | 343000 | 311625 | 308250 | 304975 | 148050 | 323625
PLANNED HOURS | 970.5 | 872.1429 | 861.4286 | 889.4286 | 432 | 915.8929
ACTUAL HOURS | 980 | 890.3571 | 880.7143 | 871.3571 | 423 | 924.6429

## PROJECT DETAILS
[Company Name]
Project Planning for Law Firms
Company Confidential
[10 empty] | PLANNING | [5 empty] | ACTUALS
PROJECT NAME | PROJECT TYPE | ESTIMATED START | ESTIMATED FINISH | ACTUAL START | ACTUAL FINISH | ESTIMATED WORK | ACTUAL WORK | ESTIMATED DURATION | ACTUAL DURATION | GENERAL PARTNER | BUSINESS LAWYER | DEFENSE LITIGATOR | INTELLECTUAL PROPERTY LAWYER | BANKRUPTCY LAWYER | ADMIN STAFF | GENERAL PARTNER 2 | BUSINESS LAWYER 2 | DEFENSE LITIGATOR 2 | INTELLECTUAL PROPERTY LAWYER 2 | BANKRUPTCY LAWYER 2 | ADMIN STAFF 2
A. Datum Corporation | Business Incorporation | 2013-06-09 | 2013-08-07 | 2013-06-29 | 2013-09-03 | 200 | 220 | 58 | 64 | 7000 | 20000 | 0 | 0 | 0 | 12500 | 7700 | 22000 | 0 | 0 | 0 | 13750
Adventure Works | Business Acquisition | 2013-06-25 | 2013-07-27 | 2013-07-15 | 2013-08-25 | 400 | 390 | 32 | 40 | 14000 | 40000 | 0 | 11000 | 0 | 20000 | 13650 | 39000 | 0 | 10725 | 0 | 19500
Alpine Ski House | Product Liability Defense | 2013-07-12 | 2013-09-19 | 2013-08-07 | 2013-10-10 | 500 | 500 | 67 | 63 | 35000 | 0 | 75000 | 0 | 0 | 18750 | 35000 | 0 | 75000 | 0 | 0 | 18750
Baldwin Museum of Science | Patent Application | 2013-07-30 | 2013-09-28 | 2013-09-14 | 2013-11-13 | 150 | 145 | 58 | 59 | 5250 | 0 | 0 | 24750 | 0 | 5625 | 5075 | 0 | 0 | 23925 | 0 | 5437.5
Blue Yonder Airlines | Employee Lawsuit | 2013-08-11 | 2013-08-21 | 2013-09-14 | 2013-09-25 | 250 | 255 | 10 | 11 | 17500 | 6250 | 30000 | 0 | 0 | 9375 | 17850 | 6375 | 30600 | 0 | 0 | 9562.5
City Power & Light | Bankruptcy | 2013-08-22 | 2013-10-02 | 2013-09-28 | 2013-10-27 | 300 | 310 | 40 | 29 | 10500 | 15000 | 0 | 0 | 27000 | 11250 | 10850 | 15500 | 0 | 0 | 27900 | 11625
Coho Vineyard | Business Incorporation | 2013-09-13 | 2013-09-23 | 2013-10-26 | 2013-10-13 | 500 | 510 | 10 | -13 | 17500 | 50000 | 0 | 0 | 0 | 31250 | 17850 | 51000 | 0 | 0 | 0 | 31875
Coho Winery | Product Liability Defense | 2013-09-21 | 2013-10-15 | 2013-10-23 | 2013-11-18 | 750 | 790 | 24 | 25 | 52500 | 0 | 112500 | 0 | 0 | 28125 | 55300 | 0 | 118500 | 0 | 0 | 29625
Coho Vineyard & Winery | Patent Application | 2013-10-15 | 2013-11-25 | 2013-11-30 | 2014-01-10 | 450 | 430 | 40 | 40 | 15750 | 0 | 0 | 74250 | 0 | 16875 | 15050 | 0 | 0 | 70950 | 0 | 16125
Contoso, Ltd. | Bankruptcy | 2013-10-26 | 2013-12-24 | 2013-11-26 | 2014-01-19 | 250 | 235 | 58 | 53 | 8750 | 12500 | 0 | 0 | 22500 | 9375 | 8225 | 11750 | 0 | 0 | 21150 | 8812.5
Contoso Pharmaceuticals | Business Acquisition | 2013-11-17 | 2014-01-15 | 2013-12-28 | 2014-02-26 | 200 | 235 | 58 | 58 | 7000 | 20000 | 0 | 5500 | 0 | 10000 | 8225 | 23500 | 0 | 6462.5 | 0 | 11750
Consolidated Messenger | Bankruptcy | 2013-12-03 | 2014-02-02 | 2014-01-14 | 2014-03-02 | 180 | 190 | 59 | 48 | 6300 | 9000 | 0 | 0 | 16200 | 6750 | 6650 | 9500 | 0 | 0 | 17100 | 7125
Fabrikam, Inc. | Patent Application | 2013-06-21 | 2014-01-18 | 2013-08-05 | 2014-03-04 | 250 | 230 | 207 | 209 | 8750 | 0 | 0 | 41250 | 0 | 9375 | 8050 | 0 | 0 | 37950 | 0 | 8625
Fourth Coffee | Product Liability Defense | 2013-12-20 | 2014-02-04 | 2014-01-27 | 2014-03-25 | 240 | 225 | 44 | 58 | 16800 | 0 | 36000 | 0 | 0 | 9000 | 15750 | 0 | 33750 | 0 | 0 | 8437.5
Graphic Design Institute | Patent Application | 2013-12-28 | 2014-03-05 | 2014-01-17 | 2014-04-10 | 320 | 305 | 67 | 83 | 11200 | 0 | 0 | 52800 | 0 | 12000 | 10675 | 0 | 0 | 50325 | 0 | 11437.5
Humongous Insurance | Business Acquisition | 2014-01-04 | 2014-03-06 | 2014-02-03 | 2014-04-06 | 550 | 565 | 62 | 63 | 19250 | 55000 | 0 | 15125 | 0 | 27500 | 19775 | 56500 | 0 | 15537.5 | 0 | 28250
Litware, Inc. | Bankruptcy | 2014-01-23 | 2014-03-07 | 2014-03-07 | 2014-04-08 | 350 | 350 | 44 | 31 | 12250 | 17500 | 0 | 0 | 31500 | 13125 | 12250 | 17500 | 0 | 0 | 31500 | 13125
Lucerne Publishing | Business Incorporation | 2014-02-05 | 2014-04-17 | 2014-03-07 | 2014-06-03 | 200 | 205 | 72 | 86 | 7000 | 20000 | 0 | 0 | 0 | 12500 | 7175 | 20500 | 0 | 0 | 0 | 12812.5
Margie's Travel | Employee Lawsuit | 2014-02-15 | 2014-04-30 | 2014-03-26 | 2014-06-09 | 220 | 230 | 75 | 73 | 15400 | 5500 | 26400 | 0 | 0 | 8250 | 16100 | 5750 | 27600 | 0 | 0 | 8625
Northwind Traders | Bankruptcy | 2014-03-17 | 2014-05-25 | 2014-04-29 | 2014-07-01 | 600 | 560 | 68 | 62 | 21000 | 30000 | 0 | 0 | 54000 | 22500 | 19600 | 28000 | 0 | 0 | 50400 | 21000
Proseware, Inc. | Patent Application | 2014-03-29 | 2014-05-19 | 2014-05-18 | 2014-06-19 | 525 | 540 | 50 | 31 | 18375 | 0 | 0 | 86625 | 0 | 19687.5 | 18900 | 0 | 0 | 89100 | 0 | 20250
School of Fine Art | Employee Lawsuit | 2014-04-09 | 2014-04-29 | 2014-05-02 | 2014-06-04 | 180 | 190 | 20 | 32 | 12600 | 4500 | 21600 | 0 | 0 | 6750 | 13300 | 4750 | 22800 | 0 | 0 | 7125
TOTAL | [5 empty] | 7565 | 7610 | 1223 | 1205
INFO
To add a row, select the bottom-right most cell in the body of the table (not the totals row) and press Tab, or right-click where you want the row inserted and select Insert | Table Rows Above/Below.
Be sure all unused rows are deleted, as the PROJECT TOTALS PivotTable will use all of the tables cells, and otherwise would give erroneous results.
To delete this info tip, select any edge and press Delete.

## PROJECT TOTALS
[Company Name]
Project Planning for Law Firms
Company Confidential
| ESTIMATED | [5 empty] | ACTUAL
Data
PROJECT NAME | GENERAL PARTNER | BUSINESS | DEFENSE LITIGATOR | INTELLECTUAL PROPERTY | BANKRUPTCY | ADMIN STAFF | GENERAL PARTNER | BUSINESS | DEFENSE LITIGATOR | BANKRUPTCY | INTELLECTUAL PROPERTY | ADMIN STAFF
A. Datum Corporation | 7000 | 20000 | 0 | 0 | 0 | 12500 | 7700 | 22000 | 0 | 0 | 0 | 13750
Adventure Works | 14000 | 40000 | 0 | 11000 | 0 | 20000 | 13650 | 39000 | 0 | 0 | 10725 | 19500
Alpine Ski House | 35000 | 0 | 75000 | 0 | 0 | 18750 | 35000 | 0 | 75000 | 0 | 0 | 18750
Baldwin Museum of Science | 5250 | 0 | 0 | 24750 | 0 | 5625 | 5075 | 0 | 0 | 0 | 23925 | 5437.5
Blue Yonder Airlines | 17500 | 6250 | 30000 | 0 | 0 | 9375 | 17850 | 6375 | 30600 | 0 | 0 | 9562.5
City Power & Light | 10500 | 15000 | 0 | 0 | 27000 | 11250 | 10850 | 15500 | 0 | 27900 | 0 | 11625
Coho Vineyard | 17500 | 50000 | 0 | 0 | 0 | 31250 | 17850 | 51000 | 0 | 0 | 0 | 31875
Coho Vineyard & Winery | 15750 | 0 | 0 | 74250 | 0 | 16875 | 15050 | 0 | 0 | 0 | 70950 | 16125
Coho Winery | 52500 | 0 | 112500 | 0 | 0 | 28125 | 55300 | 0 | 118500 | 0 | 0 | 29625
Consolidated Messenger | 6300 | 9000 | 0 | 0 | 16200 | 6750 | 6650 | 9500 | 0 | 17100 | 0 | 7125
Contoso Pharmaceuticals | 7000 | 20000 | 0 | 5500 | 0 | 10000 | 8225 | 23500 | 0 | 0 | 6462.5 | 11750
Contoso, Ltd. | 8750 | 12500 | 0 | 0 | 22500 | 9375 | 8225 | 11750 | 0 | 21150 | 0 | 8812.5
Fabrikam, Inc. | 8750 | 0 | 0 | 41250 | 0 | 9375 | 8050 | 0 | 0 | 0 | 37950 | 8625
Fourth Coffee | 16800 | 0 | 36000 | 0 | 0 | 9000 | 15750 | 0 | 33750 | 0 | 0 | 8437.5
Graphic Design Institute | 11200 | 0 | 0 | 52800 | 0 | 12000 | 10675 | 0 | 0 | 0 | 50325 | 11437.5
Humongous Insurance | 19250 | 55000 | 0 | 15125 | 0 | 27500 | 19775 | 56500 | 0 | 0 | 15537.5 | 28250
Litware, Inc. | 12250 | 17500 | 0 | 0 | 31500 | 13125 | 12250 | 17500 | 0 | 31500 | 0 | 13125
Lucerne Publishing | 7000 | 20000 | 0 | 0 | 0 | 12500 | 7175 | 20500 | 0 | 0 | 0 | 12812.5
Margie's Travel | 15400 | 5500 | 26400 | 0 | 0 | 8250 | 16100 | 5750 | 27600 | 0 | 0 | 8625
Northwind Traders | 21000 | 30000 | 0 | 0 | 54000 | 22500 | 19600 | 28000 | 0 | 50400 | 0 | 21000
Proseware, Inc. | 18375 | 0 | 0 | 86625 | 0 | 19687.5 | 18900 | 0 | 0 | 0 | 89100 | 20250
School of Fine Art | 12600 | 4500 | 21600 | 0 | 0 | 6750 | 13300 | 4750 | 22800 | 0 | 0 | 7125
Total Result | 339675 | 305250 | 301500 | 311300 | 151200 | 320562.5 | 343000 | 311625 | 308250 | 148050 | 304975 | 323625
INFO
This PivotTable will not refresh automatically. To refresh it, select it (any cell within the PivotTable), on the PIVOTTABLE TOOLS | ANALYZE ribbon tab press Refresh. Or right-click any cell in the PivotTable and select Refresh.
To delete this info tip, select any edge and press Delete.