{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Business Plan"],"not_rendered":{"images":2},"read":"whole","date_system":"1900"}

{"sheet":"Business Plan","index":0,"n_rows":28,"n_cols":35,"rows_kept":28,"merged":[[27,2,27,29]]}
[null,"BUSINESS PLAN TEMPLATE"]
[null,"Project Plan for New Business"]
[null,"Phase 1: Strategic Plan"]
[null,"Phase 2: Define the Business"]
[]
[null,"TASKS","START","END","DAYS","2018-09-02",{"$f":"F6+1","v":"2018-09-03"},{"$f":"G6+1","v":"2018-09-04"},"2018-09-05","2018-09-06","2018-09-07","2018-09-08","2018-09-09","2018-09-10","2018-09-11","2018-09-12","2018-09-13","2018-09-14","2018-09-15","2018-09-16","2018-09-17","2018-09-18","2018-09-19","2018-09-20","2018-09-21","2018-09-22","2018-09-23","2018-09-24","2018-09-25","2018-09-26","2018-09-27","2018-09-28","2018-09-29","2018-09-30",{"$f":"AH6+1","v":"2018-10-01"}]
[null,"Phase 1: Self-Assessment"]
[null,"Define Business Vision","2015-09-02","2015-09-02",{"$f":"C8-D8","v":0}]
[null,"Identify Skills","2015-09-03","2015-09-03",{"$f":"D9-C9","v":0}]
[null,"Decide Whether to Proceed","2015-09-04","2015-09-04",{"$f":"D10-C10","v":0}]
[null,"Phase 1: Define Opportunity"]
[null,"Research Market","2015-09-05","2015-09-05",{"$f":"D12-C12","v":0}]
[null,"Conduct Interviews","2015-09-06","2015-09-10",{"$f":"D13-C13","v":4}]
[null,"Identify Needed Resources","2015-09-11","2015-09-13",{"$f":"D14-C14","v":2}]
[null,"Identify Operating Costs","2015-09-13","2015-09-14",{"$f":"D15-C15","v":1}]
[null,"Phase 1: Evaluate Potential Risks"]
[null,"Assess Market Size","2015-09-15","2015-09-17",{"$f":"D17-C17","v":2}]
[null,"Estimate Competition","2015-09-17","2015-09-18",{"$f":"D18-C18","v":1}]
[null,"Assess Needed Resources","2015-09-18","2015-09-19",{"$f":"D19-C19","v":1}]
[null,"Determine Financial Requirements","2015-09-19","2015-09-21",2]
[null,"Evaluate Profitability","2015-09-21","2015-09-22",1]
[null,"Review Strategy","2015-09-22","2015-09-23",1]
[null,"Phase 2: Define the Market"]
[null,"Access Available Research","2015-09-23","2015-09-25",{"$f":"D24-C24","v":2}]
[null,"Create Market Analysis","2015-09-26","2015-09-29",{"$f":"D25-C25","v":3}]
[null,"Implement Market Analysis","2015-09-29","2015-10-01",{"$f":"D26-C26","v":2}]
[]
[null,null,"CLICK HERE TO CREATE BUSINESS PLAN TEMPLATES IN SMARTSHEET"]